## Slide 1
Stage 1: Preparation and release
Rescue Insurance Agency
20XX Expression of Interest Process: Actuary Services
Stage 2: Evaluation
Milestone/Activity | 12.03 | 12.03 | 13.03 | 14.03 | 15.03 | 18.03 | 19.03 | 20.03 | 20.03
Drafting completed | X |  |  |  |  |  |  |  | 
Reviews |  |  |  |  |  |  |  |  | 
Procurement |  | X |  |  |  |  |  |  | 
Risk Services |  |  | X |  |  |  |  |  | 
Financial Services |  |  |  | X |  |  |  |  | 
COO’s Executive Officer |  |  |  |  | X |  |  |  | 
Release Preparation |  |  |  |  |  |  |  |  | 
Log ICT request | X |  |  |  |  |  |  |  | 
Board notification | X |  |  |  |  |  |  |  | 
Advise PR team of EOI |  | X |  |  |  |  |  |  | 
Test portal |  |  |  | X |  |  |  |  | 
Order newspaper advertisement |  |  |  |  | X |  |  |  | 
Approval and release |  |  |  |  |  |  |  |  | 
Final updates |  |  |  |  |  |  | X |  | 
Approval by COO |  |  |  |  |  |  |  | X | 
Release to market |  |  |  |  |  |  |  |  | X
Week commencing: Milestone/Activity | 20.04 | 27.04 | 03.05 | 10.05
Received documents circulated to panel | X |  |  | 
Panel review period |  | X |  | 
Panel meeting(s) |  | X |  | 
Recommendation forwarded to COO for approval |  |  | X | 
Contract negotiations |  |  | X | X
Contract finalisation |  |  |  | X
Approximately one month response period
Planned activity completion timeframe is shown by an ‘X’ against the relevant day/week
Notes: This archetype is from the open textbook ‘Visuals for influence: in project management and beyond’ by Bronte van der Hoorn. The book can be accessed here:
https://usq.pressbooks.pub/visualsforprojectmanagement/
This archetype can be reused under a Creative Commons Attribution NonCommercial ShareAlike licence.